## Sheet1
| Project Name | Agency | Community Council | Estimated Cost | Phased In Costs Completed | Funding In Hand | Additional Funding Needed | Scope | Need | Status
1 | Street Maintenance Wash Bay Facility | MOA/CBERRRSA | All | 800000 |  | 0 | 800000 | Provide a wash bay and warm storage for Eagle River Street Maintenance | Street Maintenance personnel have no place to store our maintenance records and no warm storage or vehicle washing facilities in the Eagle River Area. | Plans are complete, awaiting approval and funding for the facility.
2 | French Drain rehabilitation | MOA/CBERRRSA | All | 2100000 | 335000 | 0 | 300000 | French drainage systems in the CBERRRSA area are slowly being covered over by growth and winter sand, failure will lead to glaciation and hazardous driving conditions | Reclaim over a 7 year period to renovate the French drainage systems in the CBERRRSA area. Installation of geotextile fabric to extend the life expectancy of the drainage system. | Phase one has began in 2020 and will continue if funding is available.
3 | Pavement renovation - CBERRRSA | MOA/CBERRRSA | All | 5500000 | 0 | 0 | 1500000 | Roto mill selected streets and pave to correct deficiencies. | Roads surfaces are approaching 40 to 50 years old and will be systematically aligned for a shave and pave renovation and some concrete repairs | This is a proposed six to eight year program. No work is underway and no funding has been dedicated. Project will remain in the project listing.
4 | Snow Disposal Site - Purchase and construct | MOA/CBERRRSA | All | 5000000 | 0 | 0 | 5000000 | Procure and develop a permanent CBERRRRSA snow disposal site | Future development and dense housing has created and need for a snow disposal site facility. | CBERRRSA is currently leasing a snow site from Eklutna Inc.
5 | Starner Bridge - Replacement | MOA/CBERRRSA | Chugiak | 1500000 | 0 | 0 | 1500000 | Starner Bridge is the connection from Aurora Borealis to Chamber Lane over Peters Creek. Starner Bridge is a one lane bridge spanning Peters creek and is rated at only 3 tons. | Starner bridge is incapable of supporting any maintenance equipment or emergency response equipment. | No work is underway and no funding has been dedicated. Have a proposed plan set. Project is currently in the CBERRRSA CIP project listing and CBERRRSA has requested grant funding through the State Legislature.
6 | Oberg Pathway | MOA/CBERRRSA | Chugiak | 1000000 | 0 | 0 | 1000000 | This Project will upgrade the existing road surface status with a pathway from Oberg Fields to Deer Park intersection. | No pathway exists, drainage improvement may also be needed. | No work is underway and no funding has been dedicated. Project is currently a proposal from the Chugiak Community Council. Project will remain in the project listing until approved and funded.
7 | Citation Road- Eagle River Loop to Eagle River Lane. Full Build | MOA/CBERRRSA | Eagle River | 2250000 | 0 | 0 | 2250000 | This Project will upgrade the existing Chip Sealed Road to a collector status with Sidewalk, street lighting and Drainage improvements | No sidewalk or street lighting exists, drainage improvement are also needed. | No work is underway and no funding has been dedicated. Project is currently in the CBERRRSA CIP project listing, program priorities are approved for construction by the CBERRRSA board of supervisors. Project will remain in the project listing.
8 | Coronado Sidewalk and Drainage | MOA/CBERRRSA | Eagle River | 1350000 | 421000 | 0 | 900000 | Project will install a sidewalk and drainage improvement on Coronado from Old Glenn to Eagle River Loop via the Eagle River Loop Spur. | Connect ability for pedestrian travel and Drainge Improvements | Phase one of three has been completed from Old Glenn to Lower Sunny. Project remains on the CBERRRSA CIP project listing until funding becomes available.
9 | Business Blvd renovation | MOA/CBERRRSA | Eagle River | 1250000 | 0 | 0 | 1250000 | Project will entail shave and pave of existing asphalt surfaces, concrete repairs, and drainage improvements at Coronado intersection. | Concrete repairs and drainage correction and asphalt rutting. | No work is underway and no funding has been dedicated. Project is currently in the CBERRRSA CIP project listing, program priorities are approved for construction by the CBERRRSA board of supervisors. Project will remain in the project listing.
10 | Firehouse Lane renovation | MOA/CBERRRSA | Eagle River | 850000 | 35000 | 0 | 850000 | Project will install a sidewalk and drainage improvement on Fire House Lane from Old Eagle River Road to Eagle River Road. | No sidewalk or street lighting exists, drainage improvement are also needed. | No work is underway and no construction funding has been dedicated. Project is currently in the CBERRRSA CIP project listing, plans and SWPPP have been paid for and the project is awaiting construction due to Glenn Highway construction. Project will be delayed until 2021. Project will remain in the project listing.
11 | Farm Ave Upgrade | MOA/CBERRRSA | Eagle River | 800000 | 0 | 0 | 800000 | This Project will upgrade the existing road surface status with Sidewalk, street lighting and Drainage improvements | No sidewalk or street lighting exists, drainage improvement are also needed. | No work is underway and no funding has been dedicated. Project is currently a proposal from the Eagle River Community Council. Project will remain in the project listing until approved and funded.
12 | War Admiral Drainage Improvement and Sidewalk | MOA/CBERRRSA | Eagle River Valley | 2250000 | 1178767 | 0 | 800000 | Project will install a sidewalk and drainage improvement on War Admiral from Tradition Ave to Eagle River Loop | Connect ability for pedestrian travel and Drainge Improvements | Phase one and two of three have been completed from Tradition to Sun Eagle in 2018, Phase two from Sun Eagle to Kaskanak in 2020. Phase three remains on the CBERRRSA CIP project listing until funding becomes available.
13 | Eagle River Lane upgrade- Ptarmigan to Eagle River Road | MOA/CBERRRSA | Eagle River Valley | 1500000 | 50000 | 1000000 | 500000 | Project will install a sidewalk, street lighting, drainage, and full build road improvements on Eagle River Lane from Ptarmigan to 1st street across Eagle River Road. | Connect ability for pedestrian travel, drainage improvement, and alignment of Eagle River Lane at Eagle River Road | No work is underway, funding has been dedicated through the CBERRRSA CIP program. Project will remain in the project listing until completion.
14 | Ski Road Safety Trail | MOA/CBERRRSA | Chugiak | 800000 | 0 | 0 | 800000 | This project will construct pedestrian facilities along Ski road | Connect ability for pedestrian travel, drainage improvement | No work is underway, funding has been dedicated through the CBERRRSA CIP program. Project will remain in the project listing until completion.
15 | CBERRRSA Area Wide Aquifer Study | MOA/CBERRRSA | Area Wide | 500000 | 0 | 0 | 500000 | Comprehensive study of the Chugiak, Birchwood, Eagle River Area aquifers | Little is known of the aquifers in the area | No work is underway
16 | Oberg upgrade | MOA/CBERRRSA | Chugiak | 5800000 | 0 | 0 | 5800000 | Build to a rural collector standard (Glenn Hwy to Glacier) | This road has never been built to a collector standard | No work is underway
17 | CBERRRSA Area Wide Drainge Plan | MOA/CBERRRSA | Area Wide | 500000 | 0 | 0 | 500000 | Comprehensive study of the storm drainage in the CBERRRSA area | Development I the area has prompted a study of how to handle the increased area storm drainage | No work is underway
18 | CBERRRSA Road and Drainge Rehab | MOA/CBERRRSA | Area Wide | 30000000 | 0 | 0 | 30000000 | Construct Road and Drainge Improvement in CBERRRSA | Road and Drainge needs exist through out he service area | No work is underway
19 | Fawn Lane Upgrade | MOA/CBERRRSA | Chugiak | 1200000 | 0 | 0 | 1200000 | Upgrade road to local standard (deer circle to Maytag) | Local Road has never been built to standards | No work is underway
20 | Ski /Voyles Road Upgrade | MOA/CBERRRSA | Chugiak | 3000000 | 0 | 0 | 3000000 | Reconstruct the road to a arterial standard | The current road is not constructed adequately to meet its demands | No work is underway
21 | Reese Blvd Upgrade | MOA/CBERRRSA | Chugiak | 3000000 | 0 | 0 | 3000000 | Upgrade road to local standard (Sampson to Lake Hill) | This road has never been constructed to rural collector standards | No work is underway
22 | Glenn Hwy eastside frontage road | DOT/MOA | Chugiak | Unknown | 0 | 0 | Unknown | Construct a frontage road (North Peters Creek to Thunderbird Fall) | Frontage road is needed for improved access | No work is underway
23 | South Birchwood Loop Road Safe Child Corridor | DOT | Birchwood/Chugiak | Unknown | 0 | 0 | Unknown | Add a safe child corridor form the Glenn Hwy to the Old Glenn Hwy | The pathway in the section is not continuous and need to be connected for children walking or riding | No work is underway
24 | Chugiak HS Access Improvements | DOT/MOA | Area Wide | Unknown | 0 | 100000 | Unknown | First hand study the possibilities of improvement and costs associated with these proposed improvements | Traffic congestion and pedestrian improvements needed | Study will be conducted in 2021 through CBERRRSA Road Board and funding has yet to be determined.
25 | South Birchwood Loop Trail | DOT/MOA | Area Wide | 2000000 | 0 | 0 | 2000000 | Project would construct a trail of hardened natural organic surface | No trial exists, South Birchwood Loop is designed a collector route, this is part of the Anchorage Ped Plan | No work is underway
26 | Brecenridge Drainge Upgrade | MOA/CBERRRSA | Eagle River | 600000 | 0 | 0 | 600000 | Upgrade the draing On breckeridge, killington, and crested Butte | Drainage was atttempted to fix the Breckenridge area, however it failed to correct he Killington and Crested Butte area. | No work is Underway
27
28
29
30
|  |  |  | 73550000 | 2019767 | 1100000 | 64850000